## Gantt 2026
Task | Owner | Budget (MXN) | Open Questions | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
COLOR KEY: Green = Juan (Field) ¦ Orange = Diego (Construction & Knowledge) ¦ Blue = Ofir (Office & Strategy) ¦ Light Green = Shared ¦ Red = Milestone ¦ Yellow = Open Question
1. AGRICULTURE & LAND (NO NEW PLANTING IN 2026)
1.1 Existing 10 ha — Mapping & Inventory (April)
Clear, cut, map & count existing 10 ha — full inventory | Juan + Diego | 0 | How many mature poles exist? Current state? | bar: Apr
Count plants & poles per hectare (census) | Juan | 0 | GPS mapping needed? Cost? | bar: Apr
Assess health, density & maturity of existing bamboo | Juan + Diego | 0 | Which areas are mature enough for harvest? | bar: Apr
1.2 Prepare Next 20 ha for 2027 Planting (NO planting this year)
Select & mark next 20 ha for 2027 planting | Juan | 0 | Proximity to roads? Water? Slope? | bar: Apr
Clear & clean selected 20 ha (remove brush, debris) | Juan + workers | 0 | bar: May to Sep
Soil preparation: plowing, leveling | Juan + workers | 0 | Tractor rental needed? | bar: Aug to Nov
Identify & secure seedling supplier for 2027 order | Juan + Ofir | 0 | Which supplier? Lead time? Volume discount? | bar: Jun to Jul
Water source assessment for 30 ha (existing + new) | Juan | 0 | Sufficient? Irrigation system needed? | bar: May to Jun
1.3 First Harvest (Sep-Nov)
Selective harvest from existing 10 ha: ~1,000 poles | Juan + workers | 0 | Harvest in fall (fewer pests) | bar: Sep to Nov
Grade, mark & store harvested poles | Juan + Diego | 0 | Grading criteria? Min length/diameter? | bar: Sep to Nov
Prepare poles for treatment (cut to spec, clean) | Juan + workers | 0 | bar: Sep to Nov
1.4 Nursery Development
Build nursery infrastructure (prep for own seedlings ~2029-2030) | Diego | 300000 | bar: Jun to Sep
First propagation trial from existing root stock | Juan | 0 | Need specialist? Contact CEBAMEX? | bar: Sep to Nov
2. TREATMENT & PROCESSING
Build 10 small treatment pools (30 poles x 7 days each) | Diego | 1300000 | Materials? Local contractor or self-build? | bar: Apr to Jun
Purchase treatment chemicals (boric acid + borax) | Diego | 0 | Supplier? Annual quantity? Cost? | bar: Jun
Build drying yard | Diego | 15000 | bar: May to Jun
Treat & dry first harvest poles (~1,000 poles) | Diego + Juan | 0 | How many batches? ~7 days per cycle | bar: Sep to Dec
Document treatment process (QC protocol + photos) | Diego + Ofir | 0 | bar: Sep to Dec
Define treatment quality standards & rejection criteria | Diego | 0 | bar: Aug to Sep
3. INFRASTRUCTURE & CAPEX
Road improvements for truck access to plantation | Juan | 500000 | Which sections? Contractor needed? | bar: Apr to Jul
Upgrade Zapotal work yard | Diego | 0 | What is missing? | bar: May to Jun
Lighting, electricity, fencing for treatment area | Diego | 0 | Included in pool budget? | bar: Jun to Jul
4. LEGAL & COMPLIANCE
Verify: is the land ejidal or comunal? | Ofir + Juan | 0 | Changes entire registration process! | bar: Apr
Find local lawyer (agricultural land experience) | Ofir | 0 | Recommendations? Cost? | bar: Apr
Acta de posesion (municipal possession certificate) | Juan + Ofir | 2000 | bar: Apr to May
Escritura publica (notarized public deed) | Ofir | 20000 | How long does notary process take? | bar: May to Jul
Inscripcion RPP (public property registry) | Ofir | 10000 | bar: Jul to Sep
Certificado catastral (cadastral certificate) | Ofir | 5000 | bar: Jun to Jul
40-year lease agreement (contrato de arrendamiento) | Ofir + Juan | 8000 | Termination clauses? | bar: Aug to Oct
MILESTONE: Land title complete — unlocks FSC & due diligence | Ofir | 0 | bar: Oct
4.2 Certifications
Contact CEBAMEX — species validation | Ofir | 0 | bar: May to Jun
Obtain technical validation letter from CEBAMEX | Ofir | 15000 | Cost? Timeline? | bar: Jul to Sep
FSC gap analysis (pre-assessment) | Ofir | 25000 | Only after land title complete | bar: Nov to Dec
5. FINANCE & FUNDRAISING
Deploy bridge funding (5M MXN) | Ofir | 5000000 | Bank account? Release mechanism? | bar: Apr
Finalize interactive financial model | Ofir | 0 | bar: Apr to May
Build investor pitch deck | Ofir | 0 | bar: May to Jun
Prepare due diligence materials | Ofir | 0 | Required documents list? | bar: Jun to Aug
Company formation (SA de CV / SAPI / SPR) | Ofir | 0 | Which structure? Need lawyer | bar: May to Jul
Set up accounting system | Ofir | 0 | Local accountant? Software? | bar: Jun to Jul
Q3 quarterly report to bridge investors | Ofir | 0 | bar: Sep
6. SALES & MARKETING
6.1 Digital Assets
WhatsApp Business account + product catalog PDF | Ofir | 0 | bar: Apr
Google Business Profile (Oaxaca) | Ofir | 0 | Address for verification? | bar: Apr
Domain + business email (pacificobambu.com) | Ofir | 1500 | bar: Apr
LinkedIn Company Page | Ofir | 0 | bar: Apr to May
1-page product sheet (PDF in Spanish) | Ofir | 0 | Species, treatment, lengths, pricing, MOQ | bar: May
6.2 Brand Identity
Design brief + select designer (Workana / Behance) | Ofir | 0 | bar: Apr to May
Logo + visual identity design | Ofir | 25000 | 3 concepts, 2 revision rounds | bar: May to Jul
Business cards + letterhead | Ofir | 3000 | bar: Jul
Plantation photo + video shoot (drone + ground) | Ofir | 12000 | Local photographer? | bar: May to Jun
Bilingual website (Spanish/English, 5 pages) | Ofir | 25000 | WordPress / Webflow? | bar: Jun to Aug
Instagram launch (9+ posts before going live) | Ofir | 0 | bar: Jun to Jul
6.3 Sales Development & Client Management
Map buyers: bioclimatic architects in Oaxaca | Ofir | 0 | Colegio de Arquitectos de Oaxaca | bar: May to Jun
Map buyers: boutique hotels + restaurants (tourism) | Ofir + Diego | 0 | Puerto Escondido, Huatulco | bar: Jun to Jul
Map buyers: furniture makers + artisans | Diego | 0 | CaSa, Instituto Oaxaqueno de Artesanias | bar: Jul to Aug
Sample distribution (3-5 poles) to 5 architects | Diego + Ofir | 0 | Only after first harvest | bar: Oct to Nov
First sales: ~850 poles x 400 MXN = 340K MXN | Diego + Ofir | 0 | Payment terms? 50% upfront? | bar: Oct to Dec
Client management: order tracking + deliveries | Diego | 0 | CRM? Excel? WhatsApp Business? | bar: Oct to Dec
Logistics: cut-to-order + transport coordination | Diego + Juan | 0 | Transport provider? Cost? | bar: Oct to Dec
Customer service: technical support | Diego | 0 | bar: Oct to Dec
Build customer database + order history | Diego + Ofir | 0 | bar: Sep to Dec
Visit Expo CIHAC as attendee (October, CDMX) | Ofir | 5000 | Check exact 2026 dates | bar: Oct
YouTube: 90-second plantation tour video | Ofir | 0 | bar: Nov to Dec
7. CARBON CREDITS
Research active carbon aggregators in Mexico | Ofir | 0 | 3Degrees? South Pole? Local? | bar: May to Jun
Initial meetings with 2-3 aggregators | Ofir | 0 | Not economical below 30 ha | bar: Jul to Aug
Understand VM0042 vs VM0015 (Verra methodology) | Ofir | 0 | Need specialist? | bar: Aug to Sep
8. HR & TEAM
Hire 2 permanent field workers | Juan | 0 | 600 MXN/day x 25 days x 12 months | bar: Apr to May
Define roles & responsibilities (Juan, Diego, Ofir) | Ofir | 0 | bar: Apr
Employment contracts + IMSS registration | Ofir + Juan | 0 | Need lawyer/accountant? | bar: May to Jun
Worker training: clearing & land prep techniques | Juan | 0 | bar: May
Worker training: pool treatment process | Diego | 0 | bar: Aug to Sep
9. PARTNER TASK SUMMARY
JUAN: On-site field manager (Candelaria). Daily ops, workers, clearing 20 ha, harvest, roads, nursery | Juan | 0
DIEGO: Construction & knowledge. Builds pools/structures, treatment protocols, QC, client mgmt, orders | Diego | 0
OFIR: Strategy & office. Finance, fundraising, legal, marketing, branding, digital, certifications | Ofir | 0
RICK: Financial partner — no operational role | Rick | 0

## Gantt 2027
Task | Owner | Budget (MXN) | Open Questions | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. AGRICULTURE — FIRST NEW PLANTING YEAR
Order 10,000 seedlings for 20 ha (external supplier) | Juan + Ofir | 350000 | Supplier identified in 2026? Volume discount? | bar: Jan to Mar
Final soil prep for 20 ha (cleared in 2026) | Juan + workers | 0 | bar: Mar to Apr
PLANT 20 new ha (May-August) — FIRST NEW PLANTING | Juan + workers | 0 | bar: May to Aug
MILESTONE: 30 ha cumulative (10 existing + 20 new) | Juan | 0 | bar: Aug
Irrigation & monitoring of new seedlings | Juan + workers | 0 | bar: May to Dec
Ongoing maintenance: existing 10 ha | Juan + workers | 0 | bar: Jan to Dec
Harvest from base 10 ha (yr 6): ~3,000 gross poles | Juan + workers | 0 | bar: Sep to Nov
Continue nursery propagation — prep for own seedlings | Juan | 0 | How many baby bamboo growing? | bar: Jan to Dec
2. TREATMENT & PROCESSING
Treat + dry 2,550 net poles | Diego + Juan | 0 | ~5 full cycles of all 10 pools | bar: Sep to Dec
Upgrade QC: tagging + tracking system | Diego | 0 | bar: Feb to Mar
3. INFRASTRUCTURE
Warehouse Phase 1 — El Azulillo | Diego | 130000 | bar: Jan to Apr
Bamboo cabin + kitchen (on-site) | Diego + Juan | 120000 | bar: Apr to Jun
Vehicles: truck + 2 pickups | Ofir | 3000000 | New/used? Leasing? | bar: May to Jun
4. FINANCE
Quarterly reports to bridge investors (Q1, Q2, Q3) | Ofir | 0 | bar: Mar; Jun; Sep
Annual summary + major round prep materials | Ofir | 0 | 1 year of real data | bar: Nov to Dec
Begin investor conversations for 2028 major round | Ofir | 0 | How much? What equity %? | bar: Sep to Dec
5. SALES & CLIENT MANAGEMENT
Sell 2,550 poles x 400 MXN = 1,020,000 MXN | Diego + Ofir | 0 | bar: Sep to Dec
Expand to Puebla & Veracruz buyers | Ofir + Diego | 0 | bar: Jul to Oct
Partner with 3+ architects (flagship projects) | Ofir + Diego | 0 | bar: May to Aug
Ongoing client management + repeat orders | Diego | 0 | bar: Sep to Dec
Expand customer database: Puebla, Veracruz | Diego + Ofir | 0 | bar: Jul to Dec
Create case study from first project | Ofir | 0 | Need client permission | bar: Nov to Dec
6. CERTIFICATIONS
FSC formal audit (if gap analysis passed) | Ofir | 60000 | Rainforest Alliance / SCS / Bureau Veritas | bar: Jan to Jun
MILESTONE: FSC certificate obtained | Ofir | 0 | bar: Jun
Early ASTM testing (prep for US export) | Ofir | 0 | Which lab in Mexico? | bar: Jul to Sep
7. CARBON
Sign aggregator contract (3yr + exit clause) | Ofir | 0 | Only sign after 30+ ha planted | bar: Jul to Aug
Begin PDD (Project Design Document) | Ofir | 0 | Project developer cost? | bar: Sep to Dec
8. TEAM
Hire permanent nursery worker | Juan | 156000 | Annual cost | bar: Jan to Feb
Select & prepare next 25 ha for 2028 planting | Juan | 0 | bar: Sep to Dec

## Gantt 2028-2032
Task | Owner | Open Questions | 28Q1 | 28Q2 | 28Q3 | 28Q4 | 29Q1 | 29Q2 | 29Q3 | 29Q4 | 30Q1 | 30Q2 | 30Q3 | 30Q4 | 31Q1 | 31Q2 | 31Q3 | 31Q4 | 32Q1 | 32Q2 | 32Q3 | 32Q4
AGRICULTURE (Shifted: first planting 2027, full 190 ha by 2033)
Plant 25 ha (2028) — external seedlings | Juan | bar: 28Q2 to 28Q3
Plant 25 ha (2029) — transition to own seedlings | Juan | What % internal? | bar: 29Q2 to 29Q3
Plant 30 ha (2030) — own baby bamboo | Juan | bar: 30Q2 to 30Q3
Plant 35 ha (2031) — own baby bamboo | Juan | bar: 31Q2 to 31Q3
Plant 35 ha (2032) — own baby bamboo | Juan | bar: 32Q2 to 32Q3
NOTE: Final 10 ha in 2033 to reach 190 ha total | Juan | Extends planting by 1 year vs original plan
TREATMENT
Treat 5,100 poles (2028) | Diego + Juan | bar: 28Q3 to 28Q4
Treat 10,200 poles (2029) | Diego + Juan | bar: 29Q3 to 29Q4
Treat 15,300 poles (2030) — small pool capacity limit | Diego + Juan | Last year without large pools | bar: 30Q3 to 30Q4
Build first industrial pool (2031): 2,000 poles/batch | Diego | Cost? Supplier? | bar: 31Q1 to 31Q2
Scale to 3 large pools (2032) | Diego | bar: 32Q1 to 32Q2
FINANCE
MILESTONE: Close major round H1 2028 (~18M MXN) | Ofir | Final amount + equity? | bar: 28Q1 to 28Q2
Ongoing quarterly investor reports | Ofir | bar: 28Q1 to 32Q4
MILESTONE: 2030 — first cash-positive year | All | bar: 30Q4
Begin dividend distributions (2030+) | Ofir | bar: 30Q4 to 32Q4
SALES & CLIENT MANAGEMENT
Sell 5,100 poles (2028) = 2.04M MXN | Diego + Ofir | bar: 28Q3 to 28Q4
Sell 10,200 poles (2029) = 4.08M MXN | Diego + Ofir | bar: 29Q3 to 29Q4
Expand to national market: CDMX, Guadalajara | Ofir + Diego | bar: 29Q1 to 30Q4
Booth at Expo CIHAC (2028/2030) | Ofir + Diego | ~35K MXN | bar: 28Q3; 30Q3
CERTIFICATIONS
ASTM testing (export prep) | Ofir | bar: 28Q1 to 28Q4
MILESTONE: Verra first credit issuance (~2029) | Ofir | 18 months after registration | bar: 29Q4
Begin ICC-ES certification (2031) — 2.5M MXN | Ofir | Funded from revenue | bar: 31Q1 to 32Q4
US trade shows: Greenbuild, PCBC (2031+) | Ofir + Diego | bar: 31Q3 to 31Q4; 32Q3 to 32Q4
CARBON
Verra PDD + baseline measurement | Ofir | 350-700K MXN from major round | bar: 28Q1 to 28Q4
Verra validation (third-party audit) | Ofir | bar: 29Q1 to 29Q3
Self-manage vs aggregator decision (2032) | Ofir | bar: 32Q1 to 32Q2
INFRASTRUCTURE
Platform + warehouse expansion (2028) | Diego | 80K MXN | bar: 28Q1 to 28Q2
Warehouse Phase 2 — Zapotal (2029) | Diego | 130K MXN | bar: 29Q1 to 29Q2
Showroom + offices (2029) | Diego + Ofir | 500K MXN | bar: 29Q2 to 29Q4
TEAM
Hire: nursery manager + 2 field workers (2028) | Juan | Team = 8 | bar: 28Q1 to 28Q2
Hire: QC + warehouse manager (2029) | Juan + Diego | Team = ~12 | bar: 29Q1 to 29Q2
Scale to 15-18 employees (2031) | Juan + Diego | bar: 31Q1 to 31Q2

## Open Questions
# | Topic | Question | Owner | Urgency | Answer
1 | Land | Is the land ejidal or comunal? | Ofir + Juan | Urgent
2 | Land | Current registration status — what exists? | Juan | Urgent
3 | Seedlings | Supplier for 2027 planting? Lead time? | Juan | Urgent
4 | Seedlings | Seedling survival rate? | Juan | Medium
5 | Agriculture | GPS mapping of 10 ha — needed? | Juan + Ofir | Medium
6 | Agriculture | Water source for 30 ha? Irrigation needed? | Juan | Urgent
7 | Treatment | Large industrial pool cost (2,000 poles)? | Diego | Not urgent
8 | Treatment | Borax supplier? Annual quantity? Cost? | Diego | Medium
9 | Finance | Major round amount — 18M? 15M? 22M? | Ofir | Medium
10 | Finance | Legal structure — SA de CV? SAPI? SPR? | Ofir | Urgent
11 | Finance | Bank account — whose name? Release mechanism? | Ofir | Urgent
12 | Legal | Lawyer — who? Cost? Ag land experience? | Ofir | Urgent
13 | Sales | Payment terms? 50% upfront? | Diego + Ofir | Medium
14 | Sales | Minimum order quantity? | Diego + Ofir | Medium
15 | Sales | Existing buyer relationships? | Diego | Urgent
16 | Vehicles | Truck + 2 pickups — new/used? Leasing? | Ofir | Not urgent
17 | Certifications | CEBAMEX contact? Validation cost? | Ofir | Medium
18 | Certifications | ASTM lab in Mexico? | Ofir | Not urgent
19 | Carbon | Which aggregator? | Ofir | Not urgent
20 | Team | Worker terms? IMSS? Contract type? | Ofir + Juan | Urgent

## Partner Roles
Partner | Responsibilities | Key 2026 Tasks
Juan (Field Manager) | • On-site field manager — lives in Candelaria, present daily • Manages all field workers directly • Land clearing, soil prep, planting (from 2027) • Harvest, maintenance of all planted ha • Road access & field infrastructure • Nursery propagation management • Prepares poles for treatment & sale • Seedling procurement coordination • Local community relations | 1. Clear, map & count existing 10 ha (April) 2. Select next 20 ha for 2027 planting (April) 3. Hire 2 field workers (April-May) 4. Clear & clean 20 ha for next year (May-Sep) 5. Soil preparation of 20 ha (Aug-Nov) 6. Harvest ~1,000 poles (Sep-Nov) 7. Prepare poles for treatment 8. Start nursery propagation trial 9. Road improvements oversight 10. Identify seedling supplier for 2027
Diego (Construction & Knowledge Lead) | • Technical knowledge leader — treatment protocols & QC • Construction: builds all structures, pools, warehouses • Most experienced — bamboo constructor by trade • Treatment pool operations & oversight • Worker training on treatment process • Quality control & grading of poles • Client management & orders (jointly with Ofir) • Has the most industry connections • Logistics coordination (cut-to-order + transport) • Customer service & technical support | 1. Build 10 treatment pools (April-June) 2. Build drying yard (May-June) 3. Build nursery infrastructure (June-Sep) 4. Purchase treatment chemicals (June) 5. Define QC standards (Aug-Sep) 6. Treat & dry first harvest (Sep-Dec) 7. Map buyers: furniture + artisans 8. Client management: orders & deliveries (Oct+) 9. Build customer database 10. Document all processes
Ofir (Strategy & Office) | • Works from office — executes all business operations • Financial model, pitch deck, investor relations • Fundraising: bridge round + major round • All legal: land title, company formation, contracts • Accounting & financial reporting • Marketing, branding, digital assets • Sales strategy & buyer mapping • Client management & orders (jointly with Diego) • Certifications: FSC, CEBAMEX, Verra, ICC-ES • Carbon credit strategy • Overall strategy & partner coordination | 1. Deploy bridge funding (April) 2. Finalize financial model (April-May) 3. Digital assets: WhatsApp, LinkedIn, Google (April) 4. Find lawyer + start land registration (April) 5. Build pitch deck (May-June) 6. Brand identity + website (May-August) 7. Company formation + accounting (May-July) 8. Map architect buyers (May-August) 9. Sales with Diego (Oct-Dec) 10. CEBAMEX + FSC pre-assessment 11. Q3 investor report 12. Carbon aggregator research
Rick (Financial Partner) | • Financial partner — cash contributor • 33.33% equity (pre-dilution) • No operational role | No operational tasks.

## Milestones
Date | Milestone | Owner | What It Unlocks
Apr 2026 | Map & count existing 10 ha | Juan | Real data baseline
Apr 2026 | Deploy bridge funding (5M MXN) | Ofir | Operations enabled
Jun 2026 | 10 treatment pools built | Diego | ~15,600 poles/yr capacity
Sep 2026 | 20 ha cleared & prepped for 2027 planting | Juan | Ready for first new planting
Oct 2026 | Land title registration complete | Ofir + Juan | FSC + due diligence + lease
Dec 2026 | First sales: 340K MXN | Diego + Ofir | Market validation
Aug 2027 | 20 ha planted (30 ha cumulative) — FIRST PLANTING | Juan | Scale trajectory started
Jun 2027 | FSC certificate obtained | Ofir | Price premium + credibility
H1 2028 | Close major round (~18M MXN) | Ofir | Growth funding
Q3 2029 | First Verra carbon credits | Ofir | ESG revenue stream
2030 | First cash-positive year | All | Dividends + independence
2031 | Begin ICC-ES certification | Ofir | US market pathway
2032 | 180 ha cumulative | Juan | Near full capacity
2033 | 190 ha — planting complete | Juan | Full plantation
~2034 | ICC-ES certified — first US export | Ofir | US market ($10-12B)

## Budget 2026
Item | Amount (MXN) | Quarter | Notes
--- CAPEX ---
Treatment pools (10 x 130K) | 1300000 | Q1-Q2 | Diego builds
Road improvements | 500000 | Q1-Q2 | Juan oversees
Nursery infrastructure | 300000 | Q2-Q3 | Diego builds
Drying yard | 15000 | Q2 | Diego builds
Land title registration | 45000 | Q1-Q3 | Ofir manages
Subtotal Capex | 2160000
--- OPEX ---
2 field workers (600/day x 25 x 9 months) | 270000 | Q2-Q4 | May-December
Management salaries (3 x 50K x 9 months) | 1350000 | Q2-Q4 | 3 active partners
SG&A | 500000 | Full year
Treatment chemicals (borax) | 0 | Q3 | NEED QUOTE!
NOTE: No seedling cost in 2026 | 0 |  | Seedlings purchased in Q1 2027
--- MARKETING & BRANDING ---
Brand identity + logo | 25000 | Q1-Q2 | Designer
Photography + video | 12000 | Q1 | Local photographer
Website (bilingual) | 25000 | Q2-Q3 | WordPress / Webflow
Business cards + letterhead | 3000 | Q2
Expo CIHAC (visitor) | 5000 | Q3 | October, CDMX
--- CERTIFICATIONS ---
CEBAMEX validation | 15000 | Q2-Q3
FSC pre-assessment | 25000 | Q3-Q4 | After land title
TOTAL ESTIMATED 2026 | ~4,390,000 |  | From 5M bridge — ~610K reserve